DRAFT SUPPLY CONTRACT

Financed under the Interreg VI-A IPA Programme Croatia - Bosnia and Herzegovina - Montenegro 2021-2027,

within the project INEREP, Subsidy Contract No. HR-BA-ME00474

Contract Number: [to be inserted at contract signature stage]

Procurement reference No.: 25.02-810.2-74/26;

FINANCED FROM THE GENERAL BUDGET OF THE UNION

MAIN CONDITIONS

1.	Civil Protection Administration Republic of Srpska,

Spasovdanska 3, 71123 East Sarajevo, Republic of Srpska, Bosnia and Herzegovina,

Registration number: 4400549870000,

represented for the purposes of the signature of this contract by the authorised representative

indicated in the respective field under “SIGNATURES” below, hereinafter referred to as

“the contracting authority”,

of the one part, and

2.	[Contractor’s full official name]

Legal form: [Contractor’s official legal form]

Registration number: [Contractor’s statutory registration number or ID or passport number]

Official address: [Contractor’s full official address]

VAT: [for contractors with VAT: VAT registration number]

(‘the contractor’)

represented for the purposes of signing this contract by the authorised representative

indicated in the respective field under “SIGNATURES” below,

on the other part,

HAVE AGREED as follows:

1.	Subject matter

The title of this contract is: “Procurement of Equipment for Fire and Rescue Units in the Republic of Srpska within the INEREP Project”.

The contract shall cover the following awarded lot or lots, as specified at contract signature:

Lot 1: Supply of Fire Pick-up Vehicles with 4x4 Drive and accompanying equipment

Lot 2: Supply of Rescue Boat with Outboard Motor and Trailer

Lot 3: Supply of Personal Protective Fire-fighting Equipment Sets

This contract concerns the lot or lots awarded to the contractor under the above procurement procedure, in accordance with the tender dossier, the contractor’s tender and the notification of award.

The terms and conditions applying to this contract are laid down hereafter and in the Special Conditions and General Conditions and their annexes. They shall be deemed to form and be read and construed as an integral part of this contract in the order described in the Special Conditions.

2.	Contract value

The contract price for the awarded lot or lots is EUR [insert amount] ([insert amount in

words]), excluding VAT.

Where this contract covers only one lot, the contract price shall correspond to the price of

that lot as stated in the contractor’s Financial Offer. Where this contract covers more than

one lot awarded to the same contractor, the contract price shall correspond to the aggregate

price of all lots covered by this contract.

The contract price shall include all costs necessary for complete performance of the contract

on a DDP basis, Incoterms® 2020, except VAT, which shall be indicated separately where

applicable.

3.	Entry into force and duration

The contract shall enter into force on the date on which it is signed by the last party.

For Lot 1 and Lot 2, the period of implementation shall commence on the date of entry into

force of the contract.

For Lot 3, the period of implementation shall commence on the date on which the contracting

authority communicates to the contractor in writing the final quantities by size. That written

communication shall constitute the delivery order for Lot 3 and shall be issued no later

than 15 calendar days after the contract enters into force.

For Lot 1, the maximum period of implementation shall be 280 calendar days, starting from

the date on which the contract is signed by the last party. The delivery period shall be 250

calendar days. The vehicles shall be delivered successively in four batches of two vehicles.

The first batch shall be delivered no later than two calendar months after the commencement

date, and each subsequent batch shall be delivered at intervals not exceeding two calendar

months. All eight vehicles shall in any event be delivered no later than 250 calendar days

after the commencement date.

The period of implementation shall end on the date of issuance of the Provisional Acceptance

Certificate. The certificate shall be issued or refused within 30 calendar days of receipt of

the contractor’s complete application for provisional acceptance.

For Lot 2, the maximum period of implementation shall be 280 calendar days, starting from

the date on which the contract is signed by the last party. The delivery period shall be 250

calendar days.

The period of implementation shall end on the date of issuance of the Provisional Acceptance

Certificate. The certificate shall be issued or refused within 30 calendar days of receipt of

the contractor’s complete application for provisional acceptance.

For Lot 3, the maximum period of implementation shall be 280 calendar days, starting from

the date on which the contracting authority communicates to the contractor in writing the

final quantities by size. The contracting authority shall communicate the final quantities by

size no later than 15 calendar days after the contract enters into force. The written

communication of the final quantities by size shall constitute the delivery order for Lot 3.

The delivery period shall be 250 calendar days from the date of that communication. The

period of implementation shall end on the date of issuance of the Provisional Acceptance

Certificate. The certificate shall be issued or refused within 30 calendar days of receipt of

the contractor’s complete application for provisional acceptance.

4.	Bank account

Payments shall be made in accordance with the Special Conditions into the following bank account:

Name of bank: [insert bank name]

Exact denomination of account holder: [full name of account holder]

Bank account number: [insert bank account number].

Signatures

| For the contractor |  | For the contracting authority |  |
| --- | --- | --- | --- |
| Endorsed for financing by the European Union* * The European Union is not a party to the contract, shall not be subject to any obligation in connection therewith and shall not be involved in any dispute settlement, including arbitration proceedings, which may arise therefrom. |  |  |  |  |