# DRAFT OF SPECIAL CONDITIONS FOR EUROPEAN UNION EXTERNAL ACTIONS

# CONTENTS

IMPORTANT! These conditions amplify and supplement, if necessary, the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions.

# The subject of the contract shall be:

# the supply, delivery, unloading, siting, installation where applicable, commissioning where applicable, provision of all required documentation, certificates, warranties, user manuals, training/instructions for use where applicable, and after-sales support of the following supplies, divided into 3 lots

# Lot 1: Supply and delivery of 8 new fire pick-up vehicles with 4x4 drive and accompanying equipment for fire and rescue units in the Republic of Srpska within the INEREP Project.

# Lot 2: Supply and delivery of 1 new rescue boat with outboard motor and trailer for fire and rescue units in the Republic of Srpska within the INEREP Project.

# Lot 3: Supply and delivery of 66 new sets of personal protective fire-fighting equipment for fire and rescue units in the Republic of Srpska within the INEREP Project.

# The supplies shall be delivered on a DDP basis, Incoterms® 2020, to the delivery location specified in Article 29 of these Special Conditions.

# The contract shall cover the lot or lots awarded to the contractor and specified in the Main Conditions.

# Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

- the main conditions;

- the special conditions;

- the general conditions (Annex I);

- the technical specifications (Annex II including clarifications before the deadline for submission of tenders and minutes from the information meeting/site visit;

- the technical offer (Annex III including clarifications from the tenderer provided during tender evaluation);

- the budget breakdown (Annex IV);

- specified forms and other relevant documents (Annex V);

The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above. Addenda shall have the order of precedence of the document they are amending.

Article 2	Language of the contract

2.1	The language of the contract shall be English. Contractual correspondence, notices, requests, approvals and other formal communications between the parties shall be in English. Supporting technical documents may be submitted in English or in one of the official languages of Bosnia and Herzegovina, written in Latin script, in accordance with Article 7 of these Special Conditions.

Article 4	Communications

4.1	Communication details

The communication details of the parties are those specified in Articles 4.5 and 4.6 of these Special Conditions. Each party shall notify the other party in writing without delay of any change to its contact details.

4.4	Communication via electronic exchange system (EES)

After the entry into force of this contract, at any time during its implementation, the contracting authority may formally notify in writing the contractor that certain communications will be made by electronic means through the EU Funding & Tenders Portal or another electronic exchange system, in accordance with the applicable terms and conditions and using the forms and templates provided there.

The notification shall indicate whether all or only certain communications under the contract will take place through the electronic exchange system. The notification shall have full legal effect from the date specified therein, which shall allow a reasonable period of time for the contractor to complete all necessary steps to have access to the relevant electronic exchange system. The activation of the use of such system shall be at no additional cost for the contracting authority.

If the use of the EU Funding & Tenders Portal or another electronic exchange system is activated, any communication covered by the activation notification related to the implementation of this contract shall be made through that system, except if explicitly instructed otherwise by the contracting authority or if communication via the system is hindered by factors beyond the control of the parties.

If communication via the electronic exchange system is hindered, instructions will be provided by the contracting authority by email.

During the course of the contract, the contracting authority reserves the right to further extend the coverage of communications made through the electronic exchange system or to activate the use of other electronic exchange systems, at no additional cost for the contracting authority.

In case of discrepancy between the terms and conditions of the EU Funding & Tenders Portal or another electronic exchange system and the clauses of this contract, including its annexes, the clauses of this contract shall prevail.

4.5 and 4.6 Mail or email communication

If communications through the EU Funding & Tenders Portal or another electronic exchange system have not been activated, or if a certain type of communication is not covered by the activation notification or is not supported by the relevant system, communications shall be sent by email or, exceptionally, on paper, by mail services, to the following addresses:

Contracting authority:

Civil Protection Administration Republic of Srpska

Spasovdanska 3, 71123 East Sarajevo, Republic of Srpska, Bosnia and Herzegovina

Email: dragisa.tesanovic@rucz.vladars.rs

Contractor (or leader in the case of a joint tender):

[Full name]

[Function]

[Company name]

[Full official address]

Email: [complete]

Article 7	Supply of documents

All contractual documents shall be submitted in English.

Supporting technical documents may be submitted in English or in one of the official languages of

Bosnia and Herzegovina, written in Latin script.

Documents in any other language shall be accompanied by a translation into English.

Where both an original-language document and an English translation are submitted, the original-

language document shall be used to verify authenticity, while the English translation shall be used for

contractual interpretation and evaluation.

The contracting authority may request clarification or a certified translation where the submitted

translation is incomplete, unclear or inconsistent with the original document.

All documents submitted by the contractor shall be complete, legible and clearly linked to the relevant

lot, item, model, certificate or contractual requirement.

Article 8	Assistance with local regulations

The contractor shall be responsible for complying with all applicable laws, regulations, standards and administrative requirements necessary for the supply, delivery, import, customs clearance, registration, authorisation, licensing, certification, installation, commissioning, operation and handover of the supplies, where applicable.

The contractor shall obtain, at its own cost and responsibility, all permits, approvals, licences, certificates, authorisations and other documents required for the proper performance of the contract, unless otherwise expressly provided in the contract or the Technical Specifications.

The contracting authority shall provide reasonable assistance to the contractor, where necessary and within its competence, by issuing confirmations, providing available information or facilitating communication with relevant authorities. Such assistance shall not relieve the contractor from its obligations and responsibilities under the contract.

The contractor shall take all necessary steps in due time to ensure that the delivery, acceptance and use of the supplies are not delayed due to failure to comply with local regulations or administrative requirements.

Article 9	General obligations

9.9	No specific visibility or communication activities are required from the contractor under this contract, except for the obligation to provide the supplies and accompanying documentation in accordance with the contract, the Technical Specifications and the instructions of the contracting authority.

Any visibility and communication activities related to the European Union financing, the Programme or the INEREP Project shall be implemented by the contracting authority, unless otherwise instructed in writing by the contracting authority during the implementation of the contract.

Article 10	Origin

## 10.1	All goods purchased under this contract may originate in any country.

## For the purposes of this contract, origin means the place where the goods are mined, grown, produced or manufactured. The origin of the goods shall be determined according to the EU Customs Code or to the relevant international agreement applicable, where relevant.

Article 11	Performance guarantee

11.1	A performance guarantee shall be required for each lot.

For Lot 1, the amount of the performance guarantee shall be 10% of the total contract price for Lot 1, including any amounts stipulated in addenda to the contract.

For Lot 2, the amount of the performance guarantee shall be 10% of the total contract price for Lot 2, including any amounts stipulated in addenda to the contract.

For Lot 3, the amount of the performance guarantee shall be 10% of the total contract price for Lot 3, including any amounts stipulated in addenda to the contract.

Where the same contractor is awarded more than one lot, the performance guarantee shall correspond to the applicable percentage for each lot awarded to that contractor.

The performance guarantee shall be provided in accordance with the General Conditions and the tender dossier.

This provision is without prejudice to any advance payment guarantee that may be required if an

advance payment is requested and granted under the contract.

Article 12	Liabilities and insurance

12.1(a) The contractor shall be liable for any loss of or damage to the supplies until provisional acceptance by the contracting authority, in accordance with the General Conditions. The contractor shall take all necessary measures to protect the supplies during manufacture, transport, delivery, unloading, siting, installation, commissioning, where applicable, and handover.

12.1(b) The contractor shall be liable for any damage caused to the contracting authority, its property, staff, representatives, premises, or to third parties, where such damage results from the contractor’s acts, omissions, negligence, breach of contract or failure to comply with applicable laws, regulations, standards or contractual obligations.

No derogation from the liability limits provided in the General Conditions shall apply.

12.2(a), paragraph 1 By derogation from Article 12.2(a), paragraph 1, of the General Conditions, before the first delivery of the supplies under the relevant lot, the contractor shall ensure that itself, its personnel, its subcontractors and any person for which the contractor is answerable are adequately insured with insurance companies recognised on the international insurance market, unless the contracting authority has given its express written consent on a specific insurance company.

The insurance shall cover, where applicable, the contractor’s liability, the supplies, transport, loading, unloading, intermediate storage, delivery, siting, installation and commissioning, as well as any other activities necessary for the proper performance of the contract.

12.2(a), paragraph 2 By derogation from Article 12.2(a), paragraph 2, of the General Conditions, the contractor shall provide the contracting authority with all cover notes and/or insurance certificates showing that the contractor’s obligations relating to insurance are fully respected no later than before the first delivery of the supplies under the relevant lot.

The contracting authority may request updated, renewed or additional insurance documents at any time during the implementation of the contract.

12.2(b), paragraph 2 The supplies shall be delivered DDP - Delivered Duty Paid, to the delivery location: Civil Protection Administration Republic of Srpska, Spasovdanska 3, 71123 East Sarajevo, Republic of Srpska, Bosnia and Herzegovina in accordance with Incoterms 2020.

The contractor shall ensure adequate transport insurance for the supplies up to the following delivery location: Civil Protection Administration of the Republic of Srpska, Spasovdanska 3, 71123 East Sarajevo, Republic of Srpska, Bosnia and Herzegovina. The insurance shall cover, as appropriate, risks related to transport, loading, unloading, intermediate storage, stowage and protection, theft, loss, damage, wetting and any other risk that may affect the supplies before provisional acceptance.

The contractor shall bear all costs and risks related to transport, loading, unloading, customs clearance, import formalities, duties, taxes, insurance and delivery of the supplies up to the place of delivery, until provisional acceptance by the contracting authority, unless otherwise provided in the contract or the Technical Specifications.

All documents, certificates, declarations, catalogues, technical sheets, service plans, authorisations, manuals, registration documents and any other supporting documentation required from the contractor shall be provided in accordance with the Technical Specifications for the relevant lot.

Article 13	Programme of implementation of the tasks

13.2	The contractor shall submit to the contracting authority, for approval, a detailed programme of implementation of the tasks within 15 calendar days from the commencement date applicable to the relevant lot, as defined in Articles 18 and 19 of these Special Conditions.

The programme of implementation shall include, as applicable to the relevant lot:

a) the proposed timetable for procurement, manufacture or preparation, transport, delivery,

unloading, siting, installation, commissioning, testing and submission of the required

documentation;

b) the delivery schedule, including the quantities and proposed dates of each delivery;

c) the arrangements for technical coordination, inspection, testing and provisional acceptance;

d) the proposed personnel, equipment and resources necessary for the proper implementation

of  the contract; and

e) any other information reasonably required by the contracting authority.

For Lot 1, the programme shall include the detailed schedule for the successive delivery of the

eight vehicles in four batches of two vehicles, in accordance with Article 19 of these Special

Conditions.

For Lot 2, the programme shall include the planned date for the delivery of the rescue boat,

outboard motor and trailer, together with the required documentation, mounting, initial servicing

and other contractual obligations.

For Lot 3, the programme shall be prepared on the basis of the final quantities by size

communicated by the contracting authority in the delivery order referred to in Article 18.2.

The contracting authority shall notify the contractor of its approval, comments or required

amendments within 15 calendar days of receipt of the programme.

Approval of the programme shall not relieve the contractor of any of its obligations under the

contract and shall not amend or extend the contractual delivery periods.

No material alteration to the approved programme may be made without the prior written approval

of the contracting authority. Where progress does not comply with the approved programme, the

contracting authority may require the contractor to submit a revised programme, without prejudice

to the contractual delivery deadlines.

Article 14	Contractor’s drawings

14.1	The contractor shall provide all drawings, technical drawings, catalogues, technical sheets, manuals, instructions for use and maintenance, certificates and any other technical documentation required under the Technical Specifications for the relevant lot.

Where drawings, technical drawings, manuals or other technical documentation are required under the Technical Specifications, the contractor shall submit them to the contracting authority for review and approval in accordance with the deadlines and requirements set out in the contract and the Technical Specifications.

The contracting authority may approve the submitted documents, request clarifications, require corrections or reject them if they are incomplete, unclear or not compliant with the contract, the Technical Specifications or applicable standards.

Any approval by the contracting authority of drawings, manuals or other technical documentation shall not relieve the contractor of its responsibility for the correctness, completeness, quality, compliance and proper performance of the supplies.

All manuals, instructions for use and maintenance and other user documentation may be provided in English or in one of the official languages of Bosnia and Herzegovina, written in Latin script. Documents in any other language shall be accompanied by a translation into English.

Article 15	Sufficiency of tender prices

The price of the supplies shall be that shown on the financial offer (specimen in Annex IV).

15.1	The price of the supplies shall be that shown in the financial offer, namely the Budget Breakdown in Annex IV.

The contract price shall be deemed to include all costs necessary for the full and proper performance of the contract for the relevant lot, including, but not limited to, the costs of the supplies, production or procurement, packaging, transport, loading, unloading, customs clearance, import formalities, duties, taxes where applicable, insurance, delivery DDP - Delivered Duty Paid to the delivery locations specified in the Technical Specifications, siting, installation, commissioning where applicable, submission of all required documentation, certificates, declarations, manuals, warranties, after-sales support and any other costs necessary for the delivery and provisional acceptance of the supplies.

The contractor shall be deemed to have satisfied itself, before submitting its tender, as to all conditions and requirements affecting the performance of the contract, including delivery locations, transport requirements, applicable regulations, technical requirements, documentation requirements and all obligations set out in the tender dossier and the Technical Specifications.

No additional payment shall be made to the contractor for any cost, charge, fee, duty, tax, insurance, transport, administrative or technical requirement that was necessary for the proper performance of the contract but was not separately indicated in the financial offer.

The prices submitted by the contractor shall be fixed and not subject to revision, unless otherwise expressly provided in the contract.

Article 16	Tax and customs arrangements

16.1	The delivery terms shall be DDP, Incoterms® 2020. The contractor shall bear all costs and responsibilities relating to transport, insurance, unloading, import formalities, customs clearance, customs duties and other charges necessary for delivery. VAT shall be excluded only where a valid VAT exemption applies. The contracting authority shall provide the documentation required for the applicable VAT exemption procedure, and the contractor shall cooperate fully in implementing that procedure.

Article 17	Patents and licences

17.1	No derogation from Article 17 of the General Conditions shall apply.

The contractor shall be responsible for ensuring that the supplies, equipment, components, documentation, software, if any, licences, technical solutions and any other items delivered under the contract do not infringe any patent, licence, intellectual property right, industrial property right, copyright, trademark or any other third-party right.

Where any licence, authorisation or right of use is necessary for the lawful use, operation, maintenance or servicing of the supplies, the contractor shall provide it as part of the contract price, unless otherwise expressly provided in the contract or the Technical Specifications.

The contractor shall indemnify and hold harmless the contracting authority against any claim, damage, cost, expense or liability arising from any alleged or actual infringement of such rights in connection with the supplies delivered under the contract.

Article 18	Delivery order

18.2	The contract shall enter into force on the date on which it is signed by the last party.

For Lot 1 and Lot 2, the date of entry into force of the contract shall constitute the commencement date for the delivery of the supplies and implementation of the tasks. No separate delivery order shall be required to commence the contractual delivery period for Lot 1 or Lot 2.

Following the entry into force of the contract, the contracting authority may issue written

operational instructions for Lot 1 and Lot 2 concerning delivery locations, contact persons, access arrangements, technical coordination, documentation and other practical delivery details. Such instructions shall not change the commencement date or extend the contractual delivery periods, unless an extension is granted in accordance with the contract.

For Lot 3, the contracting authority shall issue a written delivery order communicating the final quantities of the personal protective fire-fighting equipment by size. The written communication of the final quantities by size shall constitute the delivery order and the commencement date for the delivery of the supplies and implementation of the tasks for Lot 3.

The contracting authority shall issue the delivery order for Lot 3 no later than 15 calendar days after the contract enters into force.

The delivery order for Lot 3 may also contain operational details concerning the delivery location, contact persons, packaging, labelling, documentation, inspection and other requirements necessary for the proper delivery and acceptance of the supplies.

The contractor shall acknowledge receipt of the delivery order for Lot 3 in writing without delay. Failure to acknowledge receipt shall not affect the validity of the delivery order where the contracting authority can demonstrate that it was duly communicated in accordance with Article 4 of the contract.

Any written operational instruction or delivery order issued under this Article shall be consistent with the contract and the Technical Specifications and shall not amend the contractual quantities, techical requirements, prices or delivery periods, except through an amendment or extension made in accordance with the contract.

Article 19	Period of implementation of the tasks

19.1	Lot 1

For Lot 1, the period of implementation shall commence on the date on which the contract enters into force, namely the date on which it is signed by the last party.

The total period of implementation shall be 280 calendar days, comprising:

a) a maximum period of 250 calendar days for the delivery of all eight vehicles, accompanying equipment, documentation and completion of all other obligations necessary for provisional acceptance; and

b) a period of up to 30 calendar days for the issuance or refusal of the Provisional Acceptance Certificate, calculated from the date of receipt of the contractor’s complete application for provisional acceptance.

The vehicles shall be delivered successively in four batches of two vehicles. The first batch of two vehicles shall be delivered no later than two calendar months after the commencement date. Each subsequent batch of two vehicles shall be delivered at intervals not exceeding two calendar months, and all eight vehicles shall in any event be delivered no later than 250 calendar days after the commencement date.

The period of implementation shall end on the date of issuance of the Provisional Acceptance Certificate.

19.2 Lot 2

For Lot 2, the period of implementation shall commence on the date on which the contract enters into force, namely the date on which it is signed by the last party.

The total period of implementation shall be 280 calendar days, comprising:

a) a maximum period of 250 calendar days for the delivery of the rescue boat, outboard motor and trailer, together with mounting, initial servicing, required documentation and completion of all other obligations necessary for provisional acceptance; and

b) a period of up to 30 calendar days for the issuance or refusal of the Provisional Acceptance Certificate, calculated from the date of receipt of the contractor’s complete application for provisional acceptance.

The period of implementation shall end on the date of issuance of the Provisional Acceptance Certificate.

19.3 Lot 3

For Lot 3, the period of implementation shall commence on the date on which the contracting authority communicates to the contractor, through the written delivery order referred to in Article 18.2, the final quantities of the personal protective fire-fighting equipment by size.

The contracting authority shall issue the delivery order no later than 15 calendar days after the contract enters into force.

The total period of implementation shall be 280 calendar days from the commencement date for Lot 3, comprising:

a) a maximum period of 250 calendar days for the delivery of all 66 complete sets in the final quantities by size specified in the delivery order, together with all required documentation and completion of all other obligations necessary for provisional acceptance; and

b) a period of up to 30 calendar days for the issuance or refusal of the Provisional Acceptance Certificate, calculated from the date of receipt of the contractor’s complete application for provisional acceptance.

The period of implementation shall end on the date of issuance of the Provisional Acceptance Certificate.

19.4 General provisions

For each lot, the contractor’s application for provisional acceptance shall be considered complete only when all supplies covered by the relevant application have been delivered and all required contractual and technical documentation has been submitted.

Where the application is incomplete, the contracting authority shall inform the contractor accordingly, and the 30-calendar-day period for issuance or refusal of the Provisional Acceptance Certificate shall commence only upon receipt of the completed application.

The contractor shall complete all deliveries, unloading, siting, installation, mounting, commissioning, testing and training or instructions for use, where applicable, and shall submit all certificates, declarations, manuals, warranty documents, service documentation, registration documentation and any other documents required under the contract and the Technical Specifications within the applicable 250-calendar-day delivery period.

The approved programme of implementation, delivery schedule, delivery order or other operational instructions shall not extend the contractual periods specified in this Article unless an extension is granted in accordance with Article 20 of the General Conditions.

Article 24	 Quality of supplies

24.2	Preliminary technical acceptance before delivery shall not be mandatory. The contracting authority may request preliminary inspection or examination of documentation for Lot 1 by written notice where considered necessary.

For Lot 1, the contractor shall notify the contracting authority in writing when the vehicles, superstructure and accompanying equipment are ready for preliminary technical acceptance. The notification shall be submitted sufficiently in advance and shall include all relevant technical documentation, catalogues, technical sheets, drawings, certificates and any other documents required under the Technical Specifications.

The contracting authority may carry out the preliminary technical acceptance through examination of the submitted documentation, visual inspection, technical inspection, functional check, on-site inspection, remote inspection or any combination thereof, as considered appropriate by the contracting authority.

For Lot 2 and Lot 3, preliminary technical acceptance before delivery shall not be required, unless the contracting authority requests it in writing. The compliance of the supplies shall be verified through the documentation, delivery inspection and provisional acceptance in accordance with the contract and the Technical Specifications.

Preliminary technical acceptance, where carried out, shall not constitute provisional acceptance or final acceptance of the supplies and shall not relieve the contractor of any obligation or responsibility under the contract, the Technical Specifications or applicable standards.

Article 25	Inspection and testing

25.2	The supplies shall be inspected and tested, as applicable, at the delivery location specified in the contract and the Technical Specifications

The inspection and testing shall include verification of compliance of the delivered supplies with the contract, the Technical Specifications, the technical offer, catalogues, technical sheets, certificates, declarations, manuals, where applicable, and any other documentation required under the tender dossier.

For Lot 1, inspection and testing may include, as applicable, visual inspection of the vehicles, superstructure and accompanying equipment, verification of technical characteristics, verification of installed equipment, functional testing of the pump, tanks, lighting and sound signalling, radio equipment, winch and other supplied equipment, as well as verification of documentation required for registration and use.

For Lot 2, inspection and testing may include, as applicable, visual inspection of the rescue boat, outboard motor and trailer, verification of technical characteristics, verification of installation of the motor, zero service of the motor, functional checks, and verification of documentation required for registration and navigation permit, where applicable.

For Lot 3, inspection and testing may include, as applicable, verification of quantities, sizes, certificates, declarations of conformity, test reports, labels, manuals, quality of items and compliance with the required standards and Technical Specifications.

The contracting authority may carry out inspection and testing directly or through persons authorised by it. The contractor shall provide all necessary assistance, access, documents, personnel, tools, equipment and conditions required for the inspection and testing of the supplies.

If, during inspection or testing, the supplies or any part thereof are found not to comply with the contract, the Technical Specifications or the approved technical offer, the contracting authority may reject them and require replacement, correction, completion or additional documentation at the contractor’s own cost and within the deadline set by the contracting authority.

Inspection and testing shall not constitute provisional acceptance or final acceptance of the supplies, unless expressly confirmed by the contracting authority in accordance with the contract for each lot.

Article 26	General principles

26.1	Payments shall be made in EUR.

Where payment to a contractor established in Bosnia and Herzegovina must, under applicable mandatory legislation, be made in BAM, the amount shall be calculated using the official fixed exchange rate of the Central Bank of Bosnia and Herzegovina applicable on the date of payment.

Pre-financing may be granted for Lot 1 only, at the request of the contractor, up to a maximum of 40% of the contract price for Lot 1, subject to the submission and acceptance by the contracting authority of a pre-financing guarantee in the same amount.

Pre-financing is not applicable to Lot 2 and Lot 3.

Payments shall be authorised and made by:

Civil protection administration Republic of Srpska

Spasovdanska 3

71123 East Sarajevo

Republic of Srpska, Bosnia and Herzegovina

26.3 	For Lot 1, pre-financing, where requested and granted, shall be made after the entry into force of the contract, receipt by the contracting authority of an admissible invoice and submission and acceptance of the pre-financing guarantee.

For Lot 1, the balance payment shall be made in accordance with the General Conditions, following provisional acceptance of the supplies and after receipt by the contracting authority of an admissible invoice and all documents required under the contract and the Technical Specifications.

For Lot 2 and Lot 3, the final payment to the contractor of the amounts due shall be made in accordance with the General Conditions, following provisional acceptance of the supplies and after receipt by the contracting authority of an admissible invoice and all documents required under the contract and the Technical Specifications.

26.5 	In order to obtain payments, the contractor must submit to the authority referred to in Article 26.1 above:

a) For the pre-financing payment for Lot 1, where requested and granted: the invoice and the pre-financing guarantee in the same amount as the requested pre-financing

b) For the balance payment for Lot 1, and for the 100% final payment for Lot 2 and Lot 3: the invoice, the application for the certificate of provisional acceptance, the delivery note, the certificate of provisional acceptance once issued, and all documents required under the contract and the Technical Specifications for the relevant lot, including, where applicable, certificates, declarations, catalogues, technical sheets, authorisations, manuals, warranty documents, service plans, registration documents and any other supporting documentation required for acceptance and use of the supplies.

26.9 	The contract does not include a price revision clause. The prices submitted by the contractor shall be fixed and not subject to revision, unless otherwise expressly provided in the contract.

26.10 	If the contractor, including each member of the group in case of a consortium, has an outstanding debt to the European Union, any payment may be offset against outstanding debts of any consortium member, in accordance with the applicable rules.

Article 28	Delayed payments

28.2	By derogation from Article 28.2 of the general conditions, once the deadline laid down in Article 26.3 has expired, the contractor shall, upon demand, be entitled to late-payment interest at the rate and for the period mentioned in the general conditions. The demand must be submitted within two months of receiving late payment.

Article 29	Delivery

29.1 	The applicable delivery term shall be DDP – Delivered Duty Paid, Incoterms® 2020.

29.2	The supplies shall be delivered DDP – Delivered Duty Paid, Incoterms® 2020, to the Civil Protection Administration of the Republic of Srpska, Spasovdanska 3, 71123 East Sarajevo, Republic of Srpska, Bosnia and Herzegovina. The contracting authority may subsequently communicate contact persons, access arrangements and other operational delivery details, provided that such instructions do not change the agreed place of delivery.

29.3 	The supplies shall be properly packed and protected for transport, loading, unloading, intermediate storage and delivery, taking into account the nature of the supplies, the means of transport, handling requirements and the need to prevent any loss, damage, wetting, corrosion, deformation or deterioration before provisional acceptance.

The contractor shall be responsible for ensuring that the packaging is suitable for the safe transport and delivery of the supplies to the place of delivery.

The packaging shall become the property of the recipient, subject to environmental considerations, unless otherwise agreed in writing by the contracting authority.

29.4  	The contact persons and operational delivery details shall be provided by the contracting authority after the entry into force of the contract by written instruction.

29.5/6/7 Each delivery shall be accompanied by all documents required under the contract and the Technical Specifications for the relevant lot, including, where applicable, the delivery note, packing list, invoice, catalogues, technical sheets, certificates, declarations, manuals, instructions for use and maintenance, warranty documents, service plans, authorisations, registration documents, customs documents and any other supporting documentation required for delivery, acceptance, registration, operation, maintenance and use of the supplies.

Documents accompanying the delivery may be provided in English or in one of the official languages of Bosnia and Herzegovina, written in Latin script. Documents in any other language shall be accompanied by a translation into English.

The packaging and/or delivery documents shall clearly indicate, as applicable, the procurement reference number, contract number, lot number, name of the contractor, name of the contracting authority, delivery location, description of the supplies, quantity, serial numbers or identification numbers where applicable, and any handling or storage instructions necessary for safe delivery and acceptance.

No visibility markings, logos or communication elements shall be placed on the supplies or packaging by the contractor unless expressly instructed in writing by the contracting authority.

Article 31	Provisional acceptance

The certificate of provisional acceptance must be issued using the template in Annex C11.

31.2 When the supplies under the relevant lot are delivered and ready for provisional acceptance, the contractor shall submit to the contracting authority an application for the certificate of provisional acceptance.

The application for provisional acceptance shall be accompanied by all documents required under the contract and the Technical Specifications for the relevant lot, including, where applicable, delivery note, packing list, certificates, declarations, catalogues, technical sheets, manuals, instructions for use and maintenance, warranty documents, service plans, authorisations, registration documents, customs documents and any other supporting documentation required for acceptance, registration, operation, maintenance and use of the supplies.

The contracting authority shall examine the delivered supplies and the accompanying documentation and may carry out inspections, tests, functional checks or any other verification considered necessary to confirm compliance with the contract, the Technical Specifications and the approved technical offer.

The contracting authority shall, within 30 calendar days from receipt of the contractor’s complete application for provisional acceptance, either:

- issue the certificate of provisional acceptance to the contractor, stating, where appropriate, any reservations; or

- reject the application, giving the reasons for rejection and specifying the actions, corrections, replacements, additional documents or other measures required for the certificate to be issued.

If the application or the accompanying documentation is incomplete, the time limit for issuing the certificate of provisional acceptance shall start from the date on which the contractor submits the complete application and all required documents.

The issuance of the certificate of provisional acceptance shall not relieve the contractor from its warranty obligations or from any other obligations under the contract.

Article 32	Warranty obligations

32.6	In addition to the warranty obligations provided under the General Conditions, the contractor shall provide all commercial, manufacturer’s and/or service warranties required under the Technical Specifications for the relevant lot.

The contractor shall ensure that all warranty documents, warranty conditions, service arrangements, authorised service information and after-sales support obligations required under the Technical Specifications are provided to the contracting authority at the latest upon provisional acceptance of the supplies.

During the applicable warranty period, the contractor shall, at its own cost and without undue delay, remedy any defect, non-conformity, malfunction or deficiency covered by the warranty, including repair, replacement, correction, servicing or provision of missing documentation, as applicable.

The commercial or manufacturer’s warranty required under the Technical Specifications shall remain valid for the period stated in the Technical Specifications or in the contractor’s tender, if longer.

32.7 The warranty under the General Conditions shall remain valid for 12 months after

provisional acceptance.

This shall be without prejudice to any longer commercial, manufacturer’s or service warranty required under the Technical Specifications or offered by the contractor.

Article 33	After-sales service

33.1	The contractor shall provide after-sales service for the supplies delivered under the relevant lot, in accordance with the contract, the Technical Specifications, the contractor’s tender and the applicable warranty obligations.

The contractor shall provide the contracting authority, at the latest upon provisional acceptance, with all relevant after-sales service information, including contact details of authorised service providers, warranty procedures, service plans where required, maintenance instructions and information on spare parts availability.

The contractor shall ensure that after-sales service is provided in a timely and professional manner and without undue delay following a written request by the contracting authority or the end user.

Article 40	Settlement of disputes

40.4	Any dispute arising out of or relating to this contract which cannot be settled amicably shall be subject to the exclusive jurisdiction of the District Commercial Court in East Sarajevo, Republic of Srpska, Bosnia and Herzegovina.

Any jurisdiction under a bilateral or multilateral investment treaty or under the ICSID rules is expressly excluded.

Article 44	Data protection

For the purpose of Article 44 of the General Conditions, for the part of the data transferred by the contracting authority to the European Commission:

(a) the controller for the processing of personal data carried out within the European Commission is the head of contracts and finance unit R4 of DG Neighbourhood and Enlargement Negotiations.

(b) the privacy statement is available at:

https://wikis.ec.europa.eu/display/ExactExternalWiki/Annexes#Annexes-AnnexesA(Ch.2):General

Processing of personal data related to the implementation of the contract by the contracting authority takes place in accordance with the national legislation of Bosnia and Herzegovina and the Republic of Srpska and with the provisions of the respective financing agreement.

To the extent that the contract covers an action financed by the European Union, the contracting authority may share communications related to the implementation of the contract with the European Commission. These exchanges shall be made to the European Commission solely for the purpose of allowing it to exercise its rights and obligations under the applicable legislative framework and under the financing agreement.

The exchanges may involve transfers of personal data, such as names, contact details, signatures and CVs, of natural persons involved in the implementation of the contract, including contractors, personnel, experts, subcontractors, insurers, guarantors, auditors and legal counsel.

Where the contractor processes personal data in the context of the implementation of the contract, the contractor shall inform the data subjects accordingly of the possible transmission of their data to the European Commission.

When personal data is transmitted to the European Commission, the European Commission processes such data in accordance with Regulation (EU) 2018/1725 of the European Parliament and of the Council of 23 October 2018 and as detailed in the specific privacy statement published at ePRAG.

- * * *